EMDC (Enterprise Mobile Device Coverage) (Sergey)

Friday, May 31, 2024

12:40 PM

  - Extended Mobile Device Coverage

    - COR: Sergey Minchenkov / Garrett Hayes

    - CO/CS: Scott Tharp / Tomeka Hall

    - Status: On Track

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received | 8/14/25 |  |
|  | APP Submitted | 8/18/25 |  |
| 11/16/25 | APP/Milestones Approved |  |  |
| 12/01/25 | Solicitation Issued |  | 11/1/25 |
| 12/16/25 | Solicitation Closes |  | 11/15/25 |
| 12/31/25 | TEP Complete |  | 12/15/25 |
| 01/15/26 | Final Proposals |  | 12/20/25 |
| 02/14/26 | Award |  | 12/31/25 |

  - Current Updates:

    - 02/10:

      - The BPAs with all three carriers - AT&T Mobility, Verizon Wireless, and T-Mobile USA - were awarded on 01/15/2026.

      - Individual EMDC call orders were awarded to AT&T on 01/28/2026 and Verizon on 01/29/2026, and performance under these call orders began on 02/01/2026.

        - Call orders will have the period of performance of 5 months ( = February to June 2026), so as to align them with the legacy T-Mobile contract's timeframe:

        - As per the previous decision, EPA will continue to utilize the legacy T-Mobile contract until its expiration on 06/30/2026.

      - In February-March 2026, COR will work on developing the follow-on call orders for all three carriers that will start on July 1, 2026 and will potentially last multiple years.

      - Please see individual tabs for "Mobile - EMDC - AT&T" and "Mobile - EMDC - Verizon" for future updates.

  - Past Updates:

    - 10/07:

      - HQAD committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy AT&T and Verizon contracts. (T-Mobile contract will run through 06/30/2026.)

      - Revised FITARA request is pending for the CIO's approval. (All other parties reviewed the request and recommended approval.)

      - COR has been working with HQAD to address their comments and make revisions to the PWS.

    - 10/07:

      - HQAD committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy AT&T and Verizon contracts. (T-Mobile contract will run through 06/30/2026.)

        - On 10/16/2025, HQAD acknowledged that they have the necessary paperwork (PWS, etc.) to begin the procurement process.

        - HQAD plans to release the solicitation to the industry by the end of October.

        - HQAD plans to conduct the TEP review in early December.

      - Revised FITARA request is pending for the CIO's approval. (All other parties, including the CTO, reviewed the request and recommended approval.)

    - 11/03:

      - HQAD is still committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy contract.

        - Revised FITARA request was approved by the CIO on 10/22/2025.

        - RFQ for the EMDC procurement was issued to the industry on 10/30/2025.

          - HQAD is working to secure three BPAs with all three major carriers (AT&T, T-Mobile, Verizon Wireless).

        - TEP is expected to be conducted in early December.

    - 11/18:

      - HQAD is still committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy contracts.

        - 10/30/2025 - RFQ for the EMDC procurement was issued to the industry.

          - HQAD is working to secure three BPAs with all three major carriers (AT&T, T-Mobile, Verizon Wireless).

        - 11/07/2025 - Vendors' follow-up questions were received by HQAD and forwarded to OITO

        - 11/12/2025 - OITO provided responses to the vendors' questions to HQAD

        - 11/17/2025 - HQAD received additional follow-up questions from the vendors

          - As of 11/18/2025, COR is working with OITO's SMEs to provide the answers

        - 12/05/2025 (tentative) - Due date for the vendors' technical and price proposals

        - 12/10/2025 (tentative) - TEP reviews will begin

        - 12/31/2025 (tentative) - EMDC contract award date.

    - 12/29:

      - On 12/16/2025, HQAD committed to awarding the EMDC Blanket Purchase Agreements with three carriers by 12/31/2025.

      - As of 12/29/2025, HQAD has not made the award yet, but the path forward that prevents lapse in mobile support is as following:

        - In January 2026, we will continue to use legacy mobile contracts:

          - We will continue to use the legacy T-Mobile contract till its expiration on 06/30/2026. On 12/22/2025, the contract was incrementally funded with $350K to cover costs through February 2026.

          - Legacy AT&T contract was extended for the month of January 2026 on 12/22/2025.

          - Legacy Verizon contract was extended for the month of January 2026 on 12/22/2025.

        - In February 2026, we will switch AT&T and Verizon to the EMDC contract:

          - PRs to initiate and fund the AT&T (PR-OFA-26-00124) and Verizon (PR-OFA-26-00125) call orders under EMDC were submitted to HQAD on 12/29/2025.

            - The goal is to award the call orders by 01/31/2026 (and HQAD had previously requested the processing time of one month for these actions).

            - Call orders will have the period of performance of 5 months ( = February to June 2026), so as to align them with the legacy T-Mobile contract.

        - In February-March 2026, COR will work on developing the follow-on call orders for all three carriers that will start on July 1, 2026 and will potentially last multiple years.

    - 01/29:

      - The BPAs with all three carriers - AT&T Mobility, Verizon Wireless, and T-Mobile USA - were awarded on 01/15/2026.

      - As of 02/01/2026, we will switch AT&T and Verizon to the EMDC contract:

        - Call orders will have the period of performance of 5 months ( = February to June 2026), so as to align them with the legacy T-Mobile contract's timeframe:

          - Call order with AT&T was enacted on 01/28/2026.

          - Call order with Verizon is expected to be enacted on 01/29/2026:

            - Verizon submitted their proposal for the call order on 01/26, and revised their proposal after a series of conversations with the COR and the Contract Specialist on 01/28.

            - COR reviewed the proposal, and submitted the evaluation to the Contract Specialist on 01/28.

            - Call order is expected to be awarded today (01/29).

          - As per the previous decision, EPA will continue to utilize the legacy T-Mobile contract until its expiration on 06/30/2026.

      - In February-March 2026, COR will work on developing the follow-on call orders for all three carriers that will start on July 1, 2026 and will potentially last multiple years.