Jan. 2026 Printer Refresh Order #1 - FY26

Wednesday, January 28, 2026

2:12 PM

  - Printer Refresh and Accessories (Dawn)

    - Current POP Expiration:   - A.R.O. 45 days

    - Ultimate Contract Expiration:  TBD

    - Contract Number: TBD

    - COR: Dawn Lamb

    - CO/CS:  Kaela Back

    - Update table below with actual milestones

  - Current Updates:

    - 4/27/2026:  Contract was awarded to The Lioce Group w delivery date of 6/12/2026.

  - Past Updates:

    - 4/14/2026:  CO solicited for 26 printers (including printers, stand, and staple finishers).

    - 4/13/2026:  COR spoke to CO who stated just received back the brand name specific.  COs next is to solicit

    - 4/2/2026:  COR waiting for contract to be awarded for new printer procurement.

    - 3/09/2026:  CO has accepted modification and awaiting PR to be processed.

    - 3/04/2026:  COR modified the PR to decrease quantity 26 printers and accessories as requested by the Service Management Division.

    - 2/27/2026:  PR still being processing and waiting to be awarded

    - 2/5/2026:  Contracting Assigned a buyer:  Kaela Back

    - 02/04/2026: PR Submitted (PR-OFA-26-00145) and routed to FCO for approval for 49 Lexmark Printers to replenish inventory.

    - 1/28/2026:  FITARA Team fixing issue w/FITARA Approval Number as code didn't work in in EAS.

    - 1/26/2026:  FITARA Approved

    - 1/12/2026:  EO Compliance form was approved for $300K for entire year of 2026.

    - 1/06/2026: COR Submitted FITARA for approval.

    - 12/29/2025:  COR submitted EO Compliance form for $300K for entire year of 2026

DicksonOne (Sergey)

Wednesday, May 27, 2026

7:30 AM

DicksonOne (Sergey)

Current POP Expiration: 28 August 2026

Ultimate Contract Expiration: 28 August 2026

Contract Number:

COR: Sergey Minchenkov/ALT. COR:  Garrett Hayes

CO:  TBD

CS:  TBD

- Current Updates:

6/1/2026

- I met with the previous contract owner (he said he was never delegated authority as a COR) 1 June 2026 and toured RTP's main building to better understand what the devices were and what they monitored.  They're small devices attached to the refrigeration units that wirelessly broadcast to a few centralized router like devices.  These devices are attached to the network and send the data to a dashboard for temperature and maintenance monitoring.

- Past Updates:

5/27/2026

General: BLUF: I know very little about this contract other than it expires in August.

I'm investigating what this contract completely entails.  The documentation I've seen doesn't appear to be current.  Prior year awards appear to be closed out and it seems like they're only ordering replacement parts each year.  I haven't seen a contract maintaining the equipment with a PoP yet.  However, when I asked the current COR, the response was "It's just an order - you're in the last option year so a clean slate going forward.  No options to exercise.  August 2026 will be the end of the PoP and we have the latest invoice for the following year ready for you."

IMCS – V (Shela)

Monday, January 05, 2026

10:20 AM

Information Management Center  Services (IMCS) - V – 3 Task Orders

COR:  Shela Poke-Williams

Please review each subtab for each Task Orders

- ABACCO Blackfish (Shela) - Contract Number: 68HERD23D0002

- AGILE - Contract Number:  68HERD23D003

- DAYCOM - Contract Number:  68HERD23D0001

Abaco Blackfish (Shela)

Thursday, January 22, 2026

1:20 PM

Information Management Center Services (IMCS) - V  -- Abaco Blackfish (Shela)

  - Current POP Expiration: 10/31/2027

  - Ultimate Contract Expiration: 10/31/2027

  - Contract Number:   68HERD23D0002 
 Task Orders:   68HERD23F0052, 68HERD23F0103

  - COR:  Shela Poke-Williams

  - CO:  Shelley Marley

  - CS:

  - Current Updates:

6/30/2026:

  - Monthly report received no problems detected

  - 4/15/2026: Received the Award of Modification P00008 to Task Order 68HERD23F0103 (Web Support for the Office of the Chief Financial Office) under Contract 68HERD23D0002 which exercises Option Period 3 (OP 3), provides funding in the amount of $107,223.60 (thereby fulling funding CLIN 3001) and extends the period of performance until 04/30/2027.

  - 3/24/2026: 80% funding notification was sent on 3/6

  - 2/27/2026: OCFO, OY2 is funded through 4/30/25. We are still waiting on a modification to exercise/fund OY3. Abaco will be sending the 85% funding notification by 3/6.

  - Past Updates:

01/28/2026:

    - Information emailed and received for updates within the task orders of the Contract Abaco from the CO.

    - Abaco Blackfish (Library Services, Records and Web Support) – 68HERD23D0002, the original amount of Abaco contract was $4,515,094.59, with pop of 11/01/2022 – 10/31/2027.

    - Two (2) task orders under Abaco Blackfish, which are as follows:

    - 68HERD23F0052, pop 3/1/2025 – 2/28/2026, total amount is $117,054.46, funding remaining - $18,679.31.

    - 68HERD23F0103, pop 5/1/2025 – 4/30/2026, total amount is $105,174.48, funding remaining - $35,058.16.

02/10/2026:

  - No updates to present.

  - 2/24:

  - This is for the IMCS V Contract concerning record keeping and storage.

  - From Ryan Philbrick, this is a follow up email to the conversation that we had yesterday, about potential cost savings at the agency. As part of an ongoing effort to quantify and document agency wide cost savings associated with centralizing paper records management activities at the National Digitization Centers (NDCs), we are requesting some assistance in obtaining some acquisition documents for the ICMS contract.

  - Specifically, we are requesting copies of the Performance Work Statements and Independent Government Cost Estimates for all active and recently completed task orders under the ICMS vehicle. We want to analyze the material in order to try to quantify the cost savings we could potentially realize by centralizing the management of paper records storage, handling, file room operations, cataloging, and other records management services.

  - 3/9:

  - Financial Summary,

3/24/2026

    - D0002 Financial Summary: Total Ceiling $4,515.094.59, amount obligated $3.902,816.83, amount originally invoiced $3,653,311.37, amount paid $3,653,311.37. Remaining approved amount $260,978.94, % of funds used 94%, ODC funds obligated $47,067.29, funds remaining $13,973.48

    - No significant difficulties encountered during this reporting period.

    - F0052 Financial Summary: Total Ceiling $ 117,054.46, amount obligated $105,056.64, amount invoiced $105,056.64, amount paid $105,056.64, % of funds used 100%, ODC funds obligated $11,997.82, ODC fund invoiced $10,882.99, ODC funds remaining $1,114.83, remaining approved amount 1,114.83.

    - Difficulties Encountered:

    - On February 2, access to the EPA Network server was down for most of the day making it impossible to search the EPA Library Catalog. Eventually it was restored. This has happened 2 other times, both for a shorter duration during this reporting period.

    - On February 24, access to EPA Duluth’s American Chemical Society’s journals (Analytical Chemistry, Chemical Research in Toxicology, and Journal Agricultural and Food Chemistry) was temporarily blocked but was restored within hours after the Librarian sent an email to ACS’s Sales Department and a phone call to ACS’s technical support.

    - F0103 Financial Summary: Total Ceiling $105,174.48, amount obligated $105,174.48, amount invoiced $87,645.40, amount paid $87,645.40, % of funds used 83%, remaining approved amount $17,529.08.

    - Difficulties Encountered

    - No significant difficulties encountered during this reporting period.

    - Anticipated Activity

    - OCFO was recently reorganized into a new office (OFA), and the Information Specialist will continue to assist in merging web content for this process. The Information Specialist is involved with a project to move policy content into an agency-wide policy catalog

4/09/2026:

  - No updates

4/21/2026:

  - No updates

4/30/2026:

  - We meet with the CO on the IMCS V contract to discuss some procedural issues, and the upcoming re-compete. I will be sending out info on the re-compete early next year.  I was asked by the CO to gently remind the TCORs of the following:

  - All PRs for option exercise should be submitted 90 days prior to end of current POP.

    - Once a task order expires, the option cannot be exercised.

    - Lack of an option exercise does not result in a stop work; it results in a task order ending.

    - A stop work cannot be used in leu of an option exercise.

    - If the option is not exercised by end of current POP, the task order must be re-competed, and no work will be done until a new task order is awarded.

  - TOCORs are responsible for tracking their funding and submitting PRs prior to funding deficit.  Incremental funding should be submitted 45 days prior to required obligation.

  - All PRs should be routed to COR for review before submitting to CO.

  - Approved Compliance memos are required to be submitted as attachments to all EAS actions.

  - I intend to set up a monthly “Office Hours” meeting in Teams soon, to allow for any issues, concerns or questions you may have. You do not need to wait for Teams office hours if you have an immediate question, feel free to call, teams chat or email me any time. Thank you so much for your ongoing support.

5/19/2026:

  - No updates

6/10/2026:

  - No updates

Agile Decision Sciences (Shela)

Thursday, January 22, 2026

1:22 PM

Information Management Center Services (IMCS) - V -- Agile Decision Sciences (Shela)

  - Current POP Expiration: 10/31/2027

  - Ultimate Contract Expiration: 10/31/2027

  - Contract Number:  68HERD23D003

  - Task Orders: 
68HERD23F0041, 68HERD23F0043, 68HERD23F0044, 68HERD23F0060, 68HERD23F0072, 68HERD23F0073, 68HERD23F0086, 68HERD23F0087, 68HERD23F0090, 68HERD23F0091, 68HERD23F0100, 68HERD23F0101, 68HERD23F0102, 68HERD23F0107, 68HERD23F0111, 68HERD23F0113, 68HERD23F0117, 68HERD23F0123, 68HERD24F0012, 68HERD25F0083, 68HERD26F0008, 68HERF26F0001

  - COR:  Shela Poke-Williams

  - CO: Ross Gillingham

  - CS:

  - Current Updates:

6/30/2026:

  - Monthly report received, no problems detected

  - Agile monthly technical report 3/28 - 4/24, no tasks orders - 68HERD23D0003

  - Past Updates:

1/28/2026:

  - Information emailed and received for updates within the task orders of the Contract Agile from the CO.

  - Agile Decision Sciences supports (Library and Records Management) - 68HERD23D0003, the original amount of the contract is $160,086,284, with pop of 11/1/2022 - 10/31/2027.

  - As of 1/28/2026, there are twenty-two (22) task orders under Agile, they are listed below:

  - 68HERD23F0041, pop 2/1/2023 – 1/31/2026 – total amount is $2,298,050.00, funding remaining - $925,326.00

  - 68HERD23F0043, pop 2/1/22023 – 1/31/2026 – total mount is $291,583.00, funding remaining - $82,231.00
 68HERD23F0044, pop 4/1/2023 – 3/31/2026 – total amount is $13,066,044.00, funding remaining - $163,719.00
 68HERD23F0060, pop 3/1/2023 – 2/28/2026 – total amount is $3,316,107.00, funding remaining - $1,351,210.00
 68HERD23F0072, pop 4/1/2023 – 3/31/2026 – total amount is $413,296.00, funding remaining - $167,536.00
 68HERD23F0073, pop 4/1/2023 – 3/31/2026 – total amount is $201.492.00, funding remaining - $8,903.00
 68HERD23F0086, pop 5/1/2025 – 4/30/2026 – total amount is $291,607.00, funding remaining - $44,135.00
 68HERD23F0087, pop 4/1/2023 - 3/31/2026 – total amount is $1,897,218.00, funding remaining - $793,699.00
 68HERD23F0090, pop 4/1/2023 - 3/31/2025 – total amount is $1,273,655.00, funding remaining - $776,942.00
 68HERD23F0091, pop 4/1/2023 – 4/30/2026 – total amount is $603,135.00, funding remaining - $244,503.00
 68HERD23F0100, pop 5/1/2023 – 4/30/2026 – total amount is $598,925.00, funding remaining - $267,569.00
 68HERD23F0101, pop 5/1/2023 – 4/30/2026 – total amount is $4,208,928.00, funding remaining, $1,687,237.00
 68HERD23F0102, pop 5/1/2023 – 4/30/2026 – total amount is $1,519,356.00, funding remaining, $837,846.00
 68HERD23F0107, pop 5/1/2023 – 4/30/2026 – total amount is $1,238,192.00, funding remaining, $565,528.00
 68HERD23F0111, pop 5/1/2023 – 4/30/2026 – total amount is $1,146,698.00, funding remaining, $476,660.00
 68HERD23F0113, pop 5/1/2023 – 4/30/2026 – total amount is $3,166,074.00, funding remaining, $1,330,144.00
 68HERD23F0117, pop 5/1/2023 – 4/30/2026 – total amount is $656,547.00, funding remaining, $309,929.00
 68HERD23F0123, pop 6/1/2023 – 5/31/2025 – total amount is $609,589.00, funding remaining, $370,480.00
 68HERD24F0012, pop 12/4/2023 – 1/3/2026 – total amount is $947,661.00, funding remaining, $573,681.00
 68HERD25F0083, pop 6/25/2025 – 6/24/2026 – total amount is $6,770,712.00, funding remaining $6,325,207.00
 68HERD26F0008, pop 4/30/2026 – 4/30/2028 – total amount is $6,046,514.00, funding remaining $5,976,514.00
 68HERF26F0001, pop 1/1/2026 – 4/30/2026 – total amount is $2,351,787.20, funding remaining $2,256,787.20.

2/10/2026:

    - No update to present

2/24/2026:

    - This is for the IMCS V Contract concerning record keeping and storage.

    - From Ryan Philbrick, this is a follow up email to the conversation that we had yesterday, about potential cost savings at the agency. As part of an ongoing effort to quantify and document agency wide cost savings associated with centralizing paper records management activities at the National Digitization Centers (NDCs), we are requesting some assistance in obtaining some acquisition documents for the ICMS contract.

    - Specifically, we are requesting copies of the Performance Work Statements and Independent Government Cost Estimates for all active and recently completed task orders under the ICMS vehicle. We want to analyze the material in order to try to quantify the cost savings we could potentially realize by centralizing the management of paper records storage, handling, file room operations, cataloging, and other records management services.

3/9/2026:

    - Task Order Contract Value $ 687,978.70

    - Task Order Funding Value $ 210,000.00

    - % of Funding Spent 35.71%

  - Funding Required to Complete EAC $ 477,978.70

3/24/2026:

  - No updates

4/09/2026:

  - No updates

04/21/2026:

  - No updates

4/30/2026:

  - We meet with the CO on the IMCS V contract to discuss some procedural issues, and the upcoming re-compete. I will be sending out info on the re-compete early next year.  I was asked by the CO to gently remind the TCORs of the following:

  - All PRs for option exercise should be submitted 90 days prior to end of current POP.

    - Once a task order expires, the option cannot be exercised.

    - Lack of an option exercise does not result in a stop work; it results in a task order ending.

    - A stop work cannot be used in leu of an option exercise.

    - If the option is not exercised by end of current POP, the task order must be re-competed, and no work will be done until a new task order is awarded.

  - TOCORs are responsible for tracking their funding and submitting PRs prior to funding deficit.  Incremental funding should be submitted 45 days prior to required obligation.

  - All PRs should be routed to COR for review before submitting to CO.

  - Approved Compliance memos are required to be submitted as attachments to all EAS actions.

  - I intend to set up a monthly “Office Hours” meeting in Teams soon, to allow for any issues, concerns or questions you may have. You do not need to wait for Teams office hours if you have an immediate question, feel free to call, teams chat or email me any time. Thank you so much for your ongoing support.

5/19/2026:

  - No updates

Daycom (Shela)

Thursday, January 22, 2026

1:22 PM

Information Management Center Services (IMCS) - V - Daycom (Shela)

  - Current POP Expiration: 10/31/2027

  - Ultimate Contract Expiration: 10/31/2027

  - Contract Number:  68HERD23D0001

  - Task Orders:    68HE0523F0013, 68HE0523F0031, 68HERD23F0112
                           68HE0823F0030, 68HE0325F0103, 68HE0726F0017

  - COR:  Shela Poke-Williams

  - CO:  Melinda McBride

  - CS:

  - Current Updates:

6/30/2026:

  - No Update

  - Past Updates:

01/28/2026:

    - Daycom (Records Management Services Superfund, and Library Services) – 68HERD23D0001, the original amount of Daycom contract was $ 203,052,645.00, with pop of 11/01/2022 – 10/31/2027. As of 1/28/2026, there are six (6) task orders under Daycom they are listed below:

    - 68HE0523F0013 Region 5 GLNPO, pop is 2/1/2023 - 12/31/2027, total amount $437,292.96, funding remaining- $184,335.84.

    - 68HE0523F0031 Region 5 Superfund, pop is 3/20/2023 - 2/29/2028, total amount $2,784,814.11, funding remaining- $1,246,318.32.

    - 68HERD23F0112 Region 4 Superfund- pop is 5/1/2023 - 4/30/2028, total amount is $2,954,240.64, funding remaining- $1,413,771.96.

    - 68HE0823F0030 Region 8 Records Management, pop is 5/15/2023 - 5/14/2028, total amount is $4,525,040.52, funding remaining- $2,028,368.21.

    - 68HE0325F0103 Region 3 Records Management, pop is 12/1/2025 - 11/30/2027, total amount is $2,119,163.04, funding remaining- $2,041,443.87.

    - 68HE0726F0017 Region 10 Library Services, pop is 12/1/2025 - 4/30/2028, total amount is $397,011.30, funding remaining- $384,478.75.

2/10/2026:

    - No update to present.

2/24/2026:

    - This is for the IMCS V Contract concerning record keeping and storage.

    - From Ryan Philbrick, this is a follow up email to the conversation that we had yesterday, about potential cost savings at the agency. As part of an ongoing effort to quantify and document agency wide cost savings associated with centralizing paper records management activities at the National Digitization Centers (NDCs), we are requesting some assistance in obtaining some acquisition documents for the ICMS contract.

    - Specifically, we are requesting copies of the Performance Work Statements and Independent Government Cost Estimates for all active and recently completed task orders under the ICMS vehicle. We want to analyze the material in order to try to quantify the cost savings we could potentially realize by centralizing the management of paper records storage, handling, file room operations, cataloging, and other records management services.

3/9/2026:

    - 1 CLIN 2001 – 01 January 2026- 31 January 2026 $49,219.58 $49,219.58

    - TOTAL DUE $49,219.58

    - Option Year 2:

    - 5/1/2025-4/30/2026

    - Remaining Funds Allocations $147,658.78

    - Total Contract Amount $590,635.00

    - Funds Allocated 33.33%

    - Total Funded $590,635.00 Total Amount Billed $49,219.58

3/24/2026:

    - No Update

4/09/2026:

    - No Update

4/21/2026:

    - No update

4/30/2026:

    - We meet with the CO on the IMCS V contract to discuss some procedural issues, and the upcoming re-compete. I will be sending out info on the re-compete early next year.  I was asked by the CO to gently remind the TCORs of the following:

    - All PRs for option exercise should be submitted 90 days prior to end of current POP.

      - Once a task order expires, the option cannot be exercised.

      - Lack of an option exercise does not result in a stop work; it results in a task order ending.

      - A stop work cannot be used in leu of an option exercise.

      - If the option is not exercised by end of current POP, the task order must be re-competed, and no work will be done until a new task order is awarded.

    - TOCORs are responsible for tracking their funding and submitting PRs prior to funding deficit.  Incremental funding should be submitted 45 days prior to required obligation.

    - All PRs should be routed to COR for review before submitting to CO.

    - Approved Compliance memos are required to be submitted as attachments to all EAS actions.

    - I intend to set up a monthly “Office Hours” meeting in Teams soon, to allow for any issues, concerns or questions you may have. You do not need to wait for Teams office hours if you have an immediate question, feel free to call, teams chat or email me any time. Thank you so much for your ongoing support.

5/19/2026:

    - No updates

6/10/2026:

    - No updates

New Awards and Recompetes

Wednesday, June 5, 2024

10:02 AM

| Upcoming Procurement | Contract End Date | PALT Start | Submit APP (PALT + 2 weeks) | Engagement Meeting | Submit SRO (APP + 2 weeks) | Submit CGER (SRO + 2 Weeks) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Adobe | 11/26/2026 | 5/26/2026 | 6/16/2026 | 5/13/2026 | 5/19/2026 | 3/20/2026 |  |
| IMCS-V | 10/31/2027 | 4/30/2026 | 4/16/2026 | 4/9/2026 | 4/2/2026 | 3/19/2026 | Confirm PALT |
| MD - T-Mobile | 6/30/2026 | 3/30/2026 | 3/16/2026 | 3/9/2026 | 3/2/2026 | 2/16/2026 |  |
| MD - Verizon | 6/30/2026 | 3/30/2026 | 3/16/2026 | 3/9/2026 | 3/2/2026 | 2/16/2026 |  |
| MD - AT&T | 6/30/2026 | 3/30/2026 | 3/16/2026 | 3/9/2026 | 3/2/2026 | 2/16/2026 |  |
| MPS | 12/31/2026 | 6/30/2026 | 6/15/2026 | 6/9/2026 | SRO submitted 6/17/2026 | EO Compliance approved on 6/12/2026 |  |
| ITI3 | 8/27/2027 | 8/27/2026 | 8/13/2026 | 8/6/2026 | 7/30/2026 | 7/16/2026 | IA |
| FedEx and UPS Shipping |  |  |  |  |  |  |  |
| Microsoft Consulting Services | 04/30/26 |  |  |  |  |  |  |

ITI-3 ()

Sunday, May 31, 2026

7:04 PM

IMCS-VI (Kim)

Sunday, May 31, 2026

7:04 PM

  - IMCS-VI

    - Current POP Expiration: 10/31/2027

    - Ultimate Contract Expiration:  TBD

    - Contract Number: TBD

    - Order Number:

    - COR:  Kim Farmer

    - CO/CS: Ross Gillingham

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
| NA | FITARA Approval Received |  |  |
| 8/1 | APP Submitted |  |  |
|  | APP/Milestones Approved |  |  |
|  | Solicitation Issued |  |  |
|  | Solicitation Closes |  |  |
|  | TEP Complete |  |  |
|  | Final Proposals |  |  |
|  | Award |  |  |

  - Current Updates

    - 6/30/2026: will be able to update and complete milestone estimates when compliance is done and initial SOW is drafted.

    - 6/23/2026: emails sent to SME for records and SME for Libraries to submit requirements for new SOW, COR working on new SOW for new contracts. COR requested input be submitted by 7/15

    - 6/16/2026:  Compliance memo Submitted

    - 6/14/2026: IGCE complete

    - 6/13/2026: Kim Farmer was assigned as Lead COR for recompete

    - 6/12/2026: Library SEMs agreed to continue with one contract for both

    - 6/10/2026: Meeting held with Libraries POCs/SME's to discuss keeping two parts together

    - No FITARA needed this is a consulting contract

    - 6/1/2026: Working on IGCE to get compliance memo started.  There are 7 task orders that did not transfer to Brad Werwick's office and we do not have access to them in EAS.  We are working to get the documentation for them in order to complete the IGCE.

    - 6/1/2026:  FITARA is not required for this recompete, determined in previous recompete that this was not an IT program

FY27 Adobe ELA

Wednesday, April 22, 2026

2:50 PM

  - Adobe ELA (Garrett)

    - Current POP Expiration: 11/26/2026

    - Ultimate Contract Expiration: 11/26/2026

    - Contract Number: TBD

    - Order Number: TBD

    - COR: Garrett Hayes /Alt:  MIchelle Cuilla

    - CO/CS: Brad Werwick/Kaela Back

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received | 4/24/2026 |  |
|  | APP Submitted | 6/16/2026 |  |
|  | APP/Milestones Approved |  | 6/29/2026 |
|  | Solicitation Issued |  | 7/05/2026 |
|  | Solicitation Closes |  | 7/10/2026 |
|  | TEP Complete |  | 7/20/2026 |
|  | Final Proposals |  | 7/30/2026 |
|  | Award |  | 11/26/2026 |

  - Current Updates

  - Date 6/30/2026

    - FITARA Approved.

    - IGCE Completed.

    - Zero dollar PR submitted:  PR-OFA-26-00304

    - EO Compliance Form Approved.

    - Market Research Completed.

    - SRO Approval – Approved 6/2.

    - APP was sent on 6/16.

  - Past Updates:

  - Date 6/2/2026:

    - FITARA Approved.

    - IGCE Completed.

    - Zero dollar PR created:  PR-OFA-26-00304

    - EO Compliance Form Approved.

    - Market Research Completed.

    - SRO Approval – Approved 6/2.

    - APP was sent on 6/16.

  - Date 5/19/2026:

    - FITARA Approved.

    - IGCE Completed.

    - Zero dollar PR Completed.

    - EO Compliance Form Approved.

    - Market Research Completed.

    - SRO-being reviewed by Garrett 5/19.

    - Meeting with Contracts 5/13.

FedEx and UPS Shipping

Tuesday, February 24, 2026

4:20 PM

  - FedEx and UPS Shipping – BPA Call Order (Adam)

    - Current POP Expiration: TBD

    - Ultimate Contract Expiration: TBD

    - Contract Number: TBD

    - COR: Adam VanEnwyck

    - CO/CS:  TBD

| EAS Date | Milestone | Actual Date | CMS Forecast |
| --- | --- | --- | --- |
|  | APP Submitted |  | 07/10/2026 |
|  | APP/Milestones Approved |  | 07/17/2026 |
|  | Solicitation Issued |  | 07/24/2026 |
|  | Solicitation Closes |  | 08/14/2026 |
|  | TEP Complete |  | 08/28/2026 |
|  | Final Proposals |  | 09/11/2026 |
|  | Award |  | 09/30/2026 |

  - Current Updates:

  - Please provide current update

  - 06/01/2026:

    - Updated CMS Forecast Dates

  - Past Updates:

  - 05/04/2026:

    - Adam reviewed proposed changes to the SOW template.  This review generated more process questions for the BPA COR.

      - Adam to submit additional questions to BPA COR (Rob Fox) by end of week

  - 04/21/2026:

    - Adam met with Terri 3/17/2026 to address questions, discuss BPA Call Order requirement, and pay current shipping invoices via CC

      - Adam to submit questions to BPA COR (Rob Fox) by end of week

  - 03/24/2026:

    - Adam met with Terri 3/17/2026 to address questions, discuss BPA Call Order requirement, and pay current shipping invoices via CC

      - Adam to submit questions to BPA COR (Rob Fox) by end of week

  - 03/02/2026:

    - Adam met with Terri's team 2/25/2026 to address questions, discuss BPA Call Order requirement

      - Terri's team to review notes and confirm questions for BPA COR.

      - Once questions are confirmed/formalized, Adam will send to BPA COR (Rob Fox)

Shredding Contract

Tuesday, April 07, 2026

8:37 AM

  - Shredding Contract (Adam)

    - Current POP Expiration: TBD

    - Ultimate Contract Expiration: TBD

    - Contract Number: TBD

    - COR: Adam VanEnwyck

    - CO/CS:  TBD

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received |  |  |
|  | APP Submitted |  |  |
|  | APP/Milestones Approved |  |  |
|  | Solicitation Issued |  |  |
|  | Solicitation Closes |  |  |
|  | TEP Complete |  |  |
|  | Final Proposals |  |  |
|  | Award |  |  |

* NOTE:  Table not updated because order likely not necessary.

  - Current Updates:

    - 6/30/2026: on Hold

  - Past Updates:

    - 6/22/2026: on Hold

    - 6/01/2026:  No new update.

    - 5/04/2026:  * No contract or purchase order anticipated at this time.  RTP Facilities has a shredding event planned for NCC in July.  COR confirmed with Facilities that the shredding event planned for the NCC will apply to confidential business information.

    - 4/21/2026:  RTP Facilities has a shredding event planned for NCC in July.  COR reached out to confirm event can accommodate confidential documents.  Awaiting confirmation.

Microsoft Consulting Services (Garrett)

Monday, June 22, 2026

9:01 AM

TrueTandem (Garrett) 
Current POP Expiration:

Ultimate Contract Expiration:

Contract Number:

COR: Garrett Hayes/ALT. COR:  Dawn Lamb

CO:  TBD

CS:  TBD

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received |  |  |
|  | APP Submitted |  |  |
|  | APP/Milestones Approved |  |  |
|  | Solicitation Issued |  |  |
|  | Solicitation Closes |  |  |
|  | TEP Complete |  |  |
|  | Final Proposals |  |  |
|  | Award |  |  |

  - Current Updates

    - 06/30/2026: PWS and IGCE complete. CGER submitted, FITARA ready to submit when CGER approval is received. APP in-progress and will be ready to submit when CGER approval is received.

  - Past Updates:

MPS Recompete

Tuesday, February 24, 2026

4:20 PM

  - MPS Recompete - (Dawn)

    - Current POP Expiration: TBD

    - Ultimate Contract Expiration: TBD

    - Contract Number: TBD

    - COR:  Dawn Lamb

    - CO/CS:  TBD

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received |  | 5/29/2026 |
|  | APP Submitted | 6/24/2026 | 6/16/2026 |
|  | APP/Milestones Approved |  | 7/16/2026 |
|  | Solicitation Issued |  | 10/14/2026 |
|  | Solicitation Closes |  | 10/31/2026 |
|  | TEP Complete |  | 11/15/2026 |
|  | Final Proposals |  | 11/30/2026 |
|  | Award |  | 12/15/2026 |

  - Current Updates:

    - 06/24/2026:

      - PR and APP was submitted together and FCO approved.

      - Still waiting on FITARA and SRO approval.

  - Past Updates:

    - 06/18/2026:

      - EO Compliance was approved on 6/12/2026.

      - Request for SRO Approval was submitted on 6/16/2026.

      - Request for FITARA approval was submitted on 6/17/2026.

      - COR is currently working on APP.

      - COR revised PWS to add task of monitoring non lexmark printers per Program's Office request.

    - 06/02/2026:

      - 6/1:  Both IT Service Branch Section and Endpoint Services Branch have concluded that the task of Print Queue Management will be added to new MPS Contract Recompete.

        - Sent draft MPS PWS out that reflects this added PWs and waiting on everyone approval by 6/3/2026.

      - EO Compliance was submitted for approval.

      - COR Is currently working on drafting the FITARA

    - 05/29/2026:

      - COR revised added additional data to reflect the back billing charges for FY26 printers that was  never billed.

      - COR finalized IGCE.  COR is now drafting EO Compliance form to submit by June 1, 2026.

      - Both Endpoint Services Branch and IT Service Branch are currently determining which contract will complete task of Print Queue Management (mtg scheduled for 6/1/2026

    - 5/27/2026:

      - COR Scheduled meeting to meet with ESSET Engineering to discuss the current section of MPS PWS included a section called "EPA Service Desk Priority Levels".  COR requested ESSET Engineer to update this section and to send a more recent copy of the "MPS Incident Ticket Handling Process"   document by Tuesday, June 2, 2026.

    - 5/21/2026:

      - COR scheduled a meeting to meet with the Endpoint Services Branch and IT Service Branch to resolve which Contract (MPS or ESSET) will be assigned the task of Print Queue Management.

        - Some discussion was skill set and cost.  That is could cost more for ESSET to complete task.

        - Program Office found the task was success having ESSET complete the task.

        - Conclusion to meeting indicated more discussions were needed as it was still not determined which contract will be completing this task.

      - COR asked for a resolution soon so recompete milestones are not delayed.

      - Separate discussion was made between Branch Chiefs.

      - COR scheduled a meeting for Monday, June 1, 2026.

    - 04/30/2026:

      - COR is pulling data from previous FY and analyzing data, while creating a draft IGCE.

      - COR requested from Service Management team data on non Lexmark printers for FY24, FY25, and FY26.

    - 04/23/2026:

      - COR is working on market research.

      - COR is researching GSA for Managed Print Service vendors.   COR will reach out to vendors is not enough information is listed.

    - 4/18/2026:  COR Submitted PWS to the Program office to get their review and edits.

    - 03/27/2026:

      - COR made minor edits to PWS.

      - COR is reviewing older notes and meeting with ESSET COR to discuss moving printers.

Legacy Contracts

Thursday, January 15, 2026

2:06 PM

Feb. 2026 Printer Accessories Order for FY26

Wednesday, February 18, 2026

10:24 AM

  - Printer Refresh and Accessories (Dawn)

    - Current POP Expiration:   - A.R.O. 45 days

    - Ultimate Contract Expiration:  - A.R.O. 45 days

    - Contract Number:   68HERF26P0034

    - COR: Dawn Lamb

    - CO/CS:  Kaela Back

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received | n/A |  |
|  | APP Submitted | n/a |  |
| 11/16/25 | APP/Milestones Approved | n/a |  |
| 12/01/25 | Solicitation Issued | n/a |  |
| 12/16/25 | Solicitation Closes | 3/2/2026 |  |
| 12/31/25 | TEP Complete | 3/20/2026 |  |
| 01/15/26 | Final Proposals | 3/20/2026 |  |
| 02/14/26 | Award | 3/20/2026 |  |

  - Current Updates:`

    - 4/1/2026:  Invoice approved by COR in IPP.

  - Past Updates:

    - 3/23/2026:  Invoice received and COR approved invoice in IPP

    - 3/20/2026:  2 staples finishers were received and confirmed by Landover Warehouse.

    - 3/20/2026:  Contract fully awarded

    - 2/18/2026:  COR submitted PR (PR-OFA-26-00302) for 2 printer accessories (internal stapler Finishers) for Lexmark 833G printer – for 2 offices (OIG and another Ofc. @ HQ).

    - 2/17/2026:  Program office expedited an order for 2 internal staple finishers and can be installed with installation.  Both finishers – one for HQ (OIG) and the other for printer in inventory.

      - COR completed necessary paperwork for PR to be submitted, waiting on FCO to give LOA.

2024 Oracle (Sergey)

Thursday, June 6, 2024

9:21 AM

  - Oracle Software Update License and Support Renewal

    - Current POP Expiration: 3/31/2025

    - Ultimate Contract Expiration: 3/31/2025

    - Contract Number: NNG15SC59B / 68HERD24F0066

    - COR: Sergey Minchenkov

    - CO/CS: Christopher Davis (CO)

  - Past Updates:

    - 7/3/2024: Pending Second Part(new CSI) award

    - 7/19/2024: Needed to answer questions from GSA to Award und NASA SEWP; Will be awarded on Friday, July 19, 2024

    - 7/30/2024: Clarity regarding new licenses (Oracle New CSI) obtained after further conversation with Oracle.  Expected award date is Friday 8/9.

    - 8/9/2024: EPAs Oracle team met with Oracle and now have clarity to complete the Order.  (est. Completion date is 8/16)

    - 8/16/2024: Oracle Part 2 New CSIs pending award just waiting on vendor to respond

    - 8/23/2024: (Part 2)  Quote came back for $750K; need to amend the PR to add additional $45K

    - 8/30/2024: (Part 2) Oracle Awarded

    - 9/6/2024: N/A

    - 9/20/2024: N/A

    - 10/8/2024:   ORACLE is scheduling a meeting soon with Technical Customer to discuss OLAP, and confirm the need.  ORACLE wants to ensure the customer is making correct decision on purchasing CSI licenses (price range 50K to 60K).

    - 10/22/2024: Meeting with Oracle schedule 10/24

    - 11/1/2024: Conducted Meeting and there is no need to add extra CSI

    - 11/15/2024: Waiting on the updated CSI list to start the APP for FY25 renewal

    - 12/20/2024: (Michelle Cuilla) awaiting updated CSI list from Tim Richards. Once CSI list is received, will be able to proceed with APPs and PRs

    - 12/31/2024: Sergey took over as COR from Michelle

  - Current Updates:

    - 01/27/2025: No new updates on this contract. See "2025 ORACLE" for the follow-on contract for calendar year 2025.

2024 Printer Refresh and Accessories (Andrew and Dawn)

Wednesday, July 31, 2024

10:55 AM

  - Printer Refresh and Accessories (Andrew and Dawn)

    - Current POP Expiration: June 2024

    - Ultimate Contract Expiration: June 2024

    - Contract Number: 68HERD24F0075

    - COR: Andrew Rhoades and Dawn Lamb

    - CO/CS: Hugo Alcantara

  - Past Updates:

    - 7/30:  A modification request to add printer accessories to the original order, 68HERD24F0075, was assigned to Dawn and myself.  I'll be working with Dawn to create a PR in EAS and submit the modification request to ITAD.  All documentation has been received and there shouldn't be any issues.  The Delivery Order was originally awarded in April or May and the printers have been getting delivered since late June.

    - 8/13:  A modification request to add printer accessories to the original order, 68HERD24F0075, was assigned to Dawn and myself.  Dawn and I have created the PR. I am reviewing and finalizing the required attachments and will submit to ITAD this week.

    - 8/26:  I am reviewing and finalizing the required attachments and will submit to ITAD this week.

    - 9/10: PR has been submitted to ITAD for review and acceptance.

    - 10/8:  No updates

    - 10/22: PR was submitted in EAS for printer accessories by Kim Farmer (while Andrew was out).

    - 11/5:  No updates.

    - 11/18:  Accessories modification was completed and issued 18 November.

    - 12/2: No updates

    - 01/02:  No updates.

  - Current Updates:

    - 1/14:  No Updates.

2025 ORACLE (Sergey)

Thursday, December 26, 2024

2:00 PM

  - Oracle Software Update License and Support Renewal

    - Current POP Expiration: 3/31/2025

    - Ultimate Contract Expiration: 3/31/2025

    - Contract Number: NNG15SC59B / 68HERD24F0066

    - COR: Sergey Minchenkov

    - CO/CS: Christopher Davis (CO)

  - Past Updates:

    - 7/3: Pending Second Part(new CSI) award

    - 7/19: Needed to answer questions from GSA to Award und NASA SEWP; Will be awarded on Friday, July 19, 2024

    - 7/30: Clarity regarding new licenses (Oracle New CSI) obtained after further conversation with Oracle.  Expected award date is Friday 8/9.

    - 8/9: EPAs Oracle team met with Oracle and now have clarity to complete the Order.  (est. Completion date is 8/16)

    - 8/16 Oracle Part 2 New CSIs pending award just waiting on vendor to respond

    - 8/23 (Part 2)  Quote came back for $750K; need to amend the PR to add additional $45K

    - 8/30 (Part 2) Oracle Awarded

    - 9/6 N/A

    - 9/20 N/A

    - 10/8:   ORACLE is scheduling a meeting soon with Technical Customer to discuss OLAP, and confirm the need.  ORACLE wants to ensure the customer is making correct decision on purchasing CSI licenses (price range 50K to 60K).

    - 10/22 Meeting with Oracle schedule 10/24

    - 11/1 Conducted Meeting and there is no need to add extra CSI

    - 11/15 Waiting on the updated CSI list to start the APP for FY25 renewal.

    - 12/20 awaiting updated CSI list from Tim Richards. Once CSI list is received, will be able to proceed with APPs and PRs.

    - 12/31  Sergey took over as the COR from Michelle.

    - 01/10 OITO/EOD expected to provide updated CSI list by COB 01/10.

    - 01/17 EOD (Tim Richards/Alan M) now expect to have CSI list complete no earlier than 1/24; the team they are waiting on for additional information has requested an extension until 1/24.  Alan also indicated there is a new requirement for a small purchase for new licenses with the renewal.  At this point, EOD estimates the renewal cost be about $4.1M, assuming an 8% mark-up of the costs from last year.

    - 01/28: Initial Oracle Procurement Package has been submitted - APP-OMS-25-00013 and $0 Planning PR PR-OMS-25-00395 have both been routed for review with IGCE at $4,720,028.80. SRO approval received. CS should finish his review sometime this week, and CO will begin his review after that.

    - 02/11: FITARA approved 02/04, and PR PR-OMS-25-00395 amended to include FITARA approval. Updated CSI list received from SME, and COR is working with SME to finalize new IGCE. CS/CO review still ongoing with goal to produce a milestone chart in the next two weeks. Funding should be available to submit funded PR shortly.

    - 02/25: Updated CSI list/IGCE provided to CO with guidance on understanding CSI List/IGCE provided by SME. CO review of APP and $0PR still ongoing. CS has submitted 1900-37 Small Business Review Form to OSDBU for review. ITAD is advising a total small business set aside, and approval is expected quickly. CS has advised that funded PR should be submitted within the next week, and COR has begun the process to submit funded PR.

    - 03/11: RFQ set to close at 09:00am on 03/17. Once quote is received, funding and LOAs can be added to PR-OMS-25-00596. EO Compliance Review form received and attached to PR. Awaiting SRO approval and quote to proceed with PR.

    - 03/25: RFQ closed 03/23. PR-OMS-25-00596 has been routed for approval. SRO pre-approval is received and signed EO Compliance Review form is attached. PR will route up through SRO for official approval. Quote sent to TPOC. License QTYs have been accepted, and agency is going back to vendor/Oracle to clarify terminations.

    - 4/08: EPA FY25 Consolidated Oracle Procurement awarded 03/31. COR confirmed with TPOC that no additional FY25 license procurement should be required.

    - 04/22: EPA FY25 Consolidated Oracle Procurement awarded 03/31. COR confirmed with TPOC that no additional FY25 license procurement should be required. Unless there is another FY25 procurement action, there should not be another update until we begin working on the FY26 procurement in September.

    - 05/06: COR confirmed with TPOC that no additional FY25 license procurement should be required. Unless there is another FY25 procurement action, there should not be another update until we begin working on the FY26 procurement in September.

    - 05/29: CPARS for the previous versions of the Oracle contract were assigned to Sergey and completed in CPARS.gov.

    - 06/17: No updates.

    - 06/30: No updates.

    - 07/14: Paid the submitted vendor invoices for the last quarter.

    - 07/31: No updates.

    - 08/12: No updates.

    - 08/27: No updates.

    - 09/10: No updates.

    - 09/22: No updates.

    - 10/07: Garrett and Sergey began developing the APP for the contract's renewal in April 2026.

    - 10/21: Garrett took the lead on developing the APP for the contract's renewal in April 2026; Sergey serves as his backup.

    - 11/03: Garrett took the lead on developing the APP for the contract's renewal in April 2026; Sergey serves as his backup.

  - Current Updates:

    - 02/10: No new updates. Garrett took the lead on developing the APP for the contract's renewal in April 2026; Sergey serves as his backup.

2025 Printer Refresh 2nd Order CY24 (Dawn)

Friday, August 30, 2024

10:50 AM

  - Printer Refresh and Accessories (Dawn)

    - Current POP Expiration:   9/5/2025 - A.R.O. 45 days

    - Ultimate Contract Expiration:

    - Contract Number: 68HERD25F0155

    - COR: Dawn Lamb

    - CO/CS: Hugo Alcantara

  - Current Updates:

    - 2/11:  COR approved invoice for Ladover Warehouse – that excluded a damaged printer.  Waiting on next steps for damaged pritner to be delivered to Landover Warehouse.

  - Past Updates:

    - 10/7:  COR created a PR mod to add installation to printer refresh order for Regions 3 and 4.  COR is waiting on Line of Accounting to come in from the Finance team.

    - 10/14:  COR created sharepoint site for all POC @ regions, HQ, and RTP to access documents pertaining to printer deliveries.

    - 10/15:  COR submitted PR to MOD existing contract award for installation in 2 regions (4 locations).  PR-OMS-26-00007 – MODP0001.

    - 10/22:  Shipping and delivery are suspended until shutdown is over.  COR is waiting to hear about delivery to only the Landover Warehouse.

    - 11/3:  Later determined that Landover Warehouse will have someone available if EPA is fully involved with the Government shutdown.  Estimated delivery for Landover Warehouse will happen the week of November 17, 2025.  Landover Warehouse has a contractor who is essential and will be notified via email with a definite delivery date.

    - 11/17:

      - COR met with Vendor to resume processing printer order and resume delivery as Government shutdown concluded.

      - Requested a document from Vendor to reflect information needed for installations (in Region 3 and 4).

      - MOD is still in pending status as Vendor has not signed the MOD for installation (Region 3 and 4).  Vendor felt the MOD needed a location correction.  Waiting for CO to respond to Vendor.

    - 11/26:

      - Printers were delivered and received @ Landover Warehosue (Hyattsville, MD), with one printer still missing as its on backorder (833).

    - 12/3:

      - Printers were delivered and received @ Region 1 (Boston, MA).  Will wait for them to scan and confirm serial #s to ensure they match what the vendor had.

      - REGION 1 - Certificate of Insurance was filled out by ATI (Carrier) and now with Region 3 Facilities team (building owner).   Printers will not be picked up by ATI - carrier (from warehouse) until an appointment is scheduled.  Waiting for Reg. 1 to give next steps.

      - Region 1 will send COR and Program Office the serial #s scanned to ensure it matches what the vendor sent.

    - 1/5:

      - Received all printers except for Philadelphia, PA Region 3.  Waiting for the carrier to confirm a date and time to deliver that should happen this week.

      - COR obtaining pictures of damaged printer and box that needs to be replaced.  This damaged printer originally was received in Landover warehouse that was transferred to the COOP.  COOP found it damaged once it was unpacked.  Waiting for next steps.

      - Received invoices for some of the printers and the COR needs to confirm the printer were received.

    - 1/21:  Damaged Printer was picked up

    - 2/5:

      - COR approved invoices for printers delivered to Region 1 (Boston), Region 3 (Philadelphia and Ft. Meade), and Region 4 (Athens, GA and Atlanta, GA).

Legacy Microsoft ELA (Kim)

Thursday, June 6, 2024

9:21 AM

  - Microsoft ELA (Kim Farmer)

    - Please include Microsoft ELA renewal milestones in the new award and recompete section

    - Current POP Expiration: 4/30/2026

    - Ultimate Contract Expiration: 4/30/2026

    - Contract Number: 68HERD23A0001

    - COR: Kim Farmer

    - CO/CS: Kaela Back

    - Future Recompete CO:  Brad

  - Current Updates:

    - 2/10:  CO received comments from OGCE concerning Limited Source Justification (LSJ) for named source.

  - Past Updates:

    - 11/3 Meeting with ITAD to map the recompete.

    - 12/15 COR submitted PR (PR-OFA-26-00141) but was delayed to routing issues.

    - 1/5:  Due to EAS routing issues, COR resubmitted (PR-OFA-26-00141) and routed to Contracting Team.  The PR is for a recompete, with an anticipated award by March 2026.

    - 1/21: Approved compliance memo received.

    - 1/28:  The PR is currently with CO, who is reviewing the APP (submitted in Sept. 2025) and Statement of Work (SOW).  The CO is new and asking the COR questions to

become more familiar with the contract.

EMDC (Enterprise Mobile Device Coverage) (Sergey)

Friday, May 31, 2024

12:40 PM

  - Extended Mobile Device Coverage

    - Move this to Legacy Contracts

    - COR: Sergey Minchenkov / Garrett Hayes

    - CO/CS: Scott Tharp / Tomeka Hall

    - Status: On Track

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
|  | FITARA Approval Received | 8/14/25 |  |
|  | APP Submitted | 8/18/25 |  |
| 11/16/25 | APP/Milestones Approved |  |  |
| 12/01/25 | Solicitation Issued |  | 11/1/25 |
| 12/16/25 | Solicitation Closes |  | 11/15/25 |
| 12/31/25 | TEP Complete |  | 12/15/25 |
| 01/15/26 | Final Proposals |  | 12/20/25 |
| 02/14/26 | Award |  | 12/31/25 |

  - Current Updates:

    - 02/10:

      - The BPAs with all three carriers - AT&T Mobility, Verizon Wireless, and T-Mobile USA - were awarded on 01/15/2026.

      - Individual EMDC call orders were awarded to AT&T on 01/28/2026 and Verizon on 01/29/2026, and performance under these call orders began on 02/01/2026.

        - Call orders will have the period of performance of 5 months ( = February to June 2026), so as to align them with the legacy T-Mobile contract's timeframe:

        - As per the previous decision, EPA will continue to utilize the legacy T-Mobile contract until its expiration on 06/30/2026.

      - In February-March 2026, COR will work on developing the follow-on call orders for all three carriers that will start on July 1, 2026 and will potentially last multiple years.

      - Please see individual tabs for "Mobile - EMDC - AT&T" and "Mobile - EMDC - Verizon" for future updates.

  - Past Updates:

    - 10/07:

      - HQAD committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy AT&T and Verizon contracts. (T-Mobile contract will run through 06/30/2026.)

      - Revised FITARA request is pending for the CIO's approval. (All other parties reviewed the request and recommended approval.)

      - COR has been working with HQAD to address their comments and make revisions to the PWS.

    - 10/07:

      - HQAD committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy AT&T and Verizon contracts. (T-Mobile contract will run through 06/30/2026.)

        - On 10/16/2025, HQAD acknowledged that they have the necessary paperwork (PWS, etc.) to begin the procurement process.

        - HQAD plans to release the solicitation to the industry by the end of October.

        - HQAD plans to conduct the TEP review in early December.

      - Revised FITARA request is pending for the CIO's approval. (All other parties, including the CTO, reviewed the request and recommended approval.)

    - 11/03:

      - HQAD is still committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy contract.

        - Revised FITARA request was approved by the CIO on 10/22/2025.

        - RFQ for the EMDC procurement was issued to the industry on 10/30/2025.

          - HQAD is working to secure three BPAs with all three major carriers (AT&T, T-Mobile, Verizon Wireless).

        - TEP is expected to be conducted in early December.

    - 11/18:

      - HQAD is still committed to awarding the revised EMDC contract by 12/31/2025, i.e. prior to the expiration of the legacy contracts.

        - 10/30/2025 - RFQ for the EMDC procurement was issued to the industry.

          - HQAD is working to secure three BPAs with all three major carriers (AT&T, T-Mobile, Verizon Wireless).

        - 11/07/2025 - Vendors' follow-up questions were received by HQAD and forwarded to OITO

        - 11/12/2025 - OITO provided responses to the vendors' questions to HQAD

        - 11/17/2025 - HQAD received additional follow-up questions from the vendors

          - As of 11/18/2025, COR is working with OITO's SMEs to provide the answers

        - 12/05/2025 (tentative) - Due date for the vendors' technical and price proposals

        - 12/10/2025 (tentative) - TEP reviews will begin

        - 12/31/2025 (tentative) - EMDC contract award date.

    - 12/29:

      - On 12/16/2025, HQAD committed to awarding the EMDC Blanket Purchase Agreements with three carriers by 12/31/2025.

      - As of 12/29/2025, HQAD has not made the award yet, but the path forward that prevents lapse in mobile support is as following:

        - In January 2026, we will continue to use legacy mobile contracts:

          - We will continue to use the legacy T-Mobile contract till its expiration on 06/30/2026. On 12/22/2025, the contract was incrementally funded with $350K to cover costs through February 2026.

          - Legacy AT&T contract was extended for the month of January 2026 on 12/22/2025.

          - Legacy Verizon contract was extended for the month of January 2026 on 12/22/2025.

        - In February 2026, we will switch AT&T and Verizon to the EMDC contract:

          - PRs to initiate and fund the AT&T (PR-OFA-26-00124) and Verizon (PR-OFA-26-00125) call orders under EMDC were submitted to HQAD on 12/29/2025.

            - The goal is to award the call orders by 01/31/2026 (and HQAD had previously requested the processing time of one month for these actions).

            - Call orders will have the period of performance of 5 months ( = February to June 2026), so as to align them with the legacy T-Mobile contract.

        - In February-March 2026, COR will work on developing the follow-on call orders for all three carriers that will start on July 1, 2026 and will potentially last multiple years.

    - 01/29:

      - The BPAs with all three carriers - AT&T Mobility, Verizon Wireless, and T-Mobile USA - were awarded on 01/15/2026.

      - As of 02/01/2026, we will switch AT&T and Verizon to the EMDC contract:

        - Call orders will have the period of performance of 5 months ( = February to June 2026), so as to align them with the legacy T-Mobile contract's timeframe:

          - Call order with AT&T was enacted on 01/28/2026.

          - Call order with Verizon is expected to be enacted on 01/29/2026:

            - Verizon submitted their proposal for the call order on 01/26, and revised their proposal after a series of conversations with the COR and the Contract Specialist on 01/28.

            - COR reviewed the proposal, and submitted the evaluation to the Contract Specialist on 01/28.

            - Call order is expected to be awarded today (01/29).

          - As per the previous decision, EPA will continue to utilize the legacy T-Mobile contract until its expiration on 06/30/2026.

      - In February-March 2026, COR will work on developing the follow-on call orders for all three carriers that will start on July 1, 2026 and will potentially last multiple years.

Infotech 2024 (Garrett)

Thursday, January 15, 2026

3:05 PM

- Infotech (Nick)

  - Current POP Expiration: 01/09/2025

  - Ultimate Contract Expiration: 01/09/2025

  - Contract Number: GS-35F-298GA /68HE0P24F0004

  - COR: Garrett Hayes

  - CO/CS: Kimberly Prather/Candice Charlton/ Rayna Brown

- Current Updates:

  - 01/27: Awarded 01/14. No updates until award effort. These will start again around 10/25.

- Past Updates:

  - 10/8 Renewal efforts will begin towards the end of October as this is due to appropriated funds being used.

  - 10/22 Pending/verification of subscriptions from Tiffany before requesting a quote.

  - 11/1 Waiting on Quote from vendor before submitting documents and PR.

  - 11/15 Submitted the funding PR for renewal for $168k

  - 12/2: No updates for the current task order.  New award status is under the New Awards and Recompetes Infotech report.

  - 12/16: No updates for the current task order.  New award status is under the New Awards and Recompetes Infotech report.

  - 12/30: Contracting office notified me that the new award will not be in place by 10 January.  They requested that a modification to extend the current PoP be created.  Contractor stated an extension is not possible, however, notified the CO that if they were willing to provide a notice of intent for the new award, they would continue services.  The CO has not responded.  I'm following up.

  - 01/14: Awarded 01/14.

PC (Laptops) Refresh (Kim)

Tuesday, January 21, 2025

9:28 AM

  - COR:  Kim Farmer

  - CO/CS:  Brad Werwick

  - Status:  On Track

High-Level Maintenance:

| EAS Date | Milestone | Actual Date | CMB Forecast |
| --- | --- | --- | --- |
| N/A | FITARA Approval Received | GSA Attached to APP |  |
| 1/15/25 | APP Submitted | 1/10/2025 |  |
| N/A | APP/Milestones Approved | N/A |  |
| 1/14/25 | Market Research Complete | 1/10/25 |  |
| 1/15/25 | Zero Dollar PR | 1/15/25 |  |
| N/A | TEP Complete | N/A (GSA Schedule) |  |
| N/A | Award | N/A (GSA Schedule) |  |

  - Past Updates:

    - 1/15:  Planning PR (PR-OMS-25-00387) submitted for approval to include IGCE that lists the quote for the entire year.  Currently with Will, and then route to Tiffany and Vaughn.

    - 1/14: Funding PR (PR-OMS-25-00379) submitted for 1st order.  Waiting on funding to be available.

    - 1/21:

      - PC refresh. Planning PR submitted last Wednesday PR-OMS-25-00387

      - Funding PR submitted last Tuesday PR-OMS-25-00379

      - Funding PR is on hold at Carla’s request. Michelle Wiggins has and is waiting on funding to be available.

      - Planning PR is in approval route, currently with the Contracting Office.

      - 1/27 SRO approved memo

      - 1/27 APP updated and resubmitted with COR nomination.

        - Planning PR is in ITAD.

    - 2/12 Waiting on Funding approval to purchase laptops.

    - 3/11:  PR is on hold and waiting on new compliance memo to be signed.

    - 4//9: Updated IGCE and count submitted for DOGE review and signature

    - 4/15: EO memo approved

    - 4/16: final package submitted to ITAD for award

    - 4/29: Awarded PR-OMS-25-00379

    - 8/18 received quote and IGCE, compliance memo submitted.

    - 8/25 Compliance memo approved

    - 8/26 PR-OMS-25-01159 submitted for final CY 25 buy $5,881,912.52

    - 9/09 Awarded

  - Current Updates:

    - 02/17/26 PR OFA-26-00301 submitted for FY 26 first laptop buy

Records Management – DC (Kim Farmer)

Thursday, June 6, 2024

9:28 AM

  - Records Management (Michelle)

    - Current POP Expiration: 4/30/2025

    - Ultimate Contract Expiration: 4/30/2028

    - Contract Number: 68HERD23F0109 / TO 0024

    - COR: Kim Farmer

    - CO/CS: Hugo Alcantra

  - Current Updates:

    - 3/11:  The Task order will not have option year 2 exercised.  A new task order is set to be issued by May 1, 2025 will include both Headquarters and RTP.

    - This task order ends 4/30/25, it will not be renewed

  - Past Updates:

    - FFP task order was fully funded on 04/25/2024 for current option period.  no further updates expected until March of 2025 for next option period award

    - 9/25/2024 no updates expected until March of 2025.

    - 1/15:  COR and CO finalized evaluation criteria after several exchanges.  COR and CMB Chief currently reviewing CO's comments for SOW, and COR will respond to CO Tuesday, 1/21.

    - 1/28:  No updates.

  - Current Updates:

    - 3/11:  The Task order will not have option year 2 exercised.  A new task order is set to be issued by May 1, 2025 will include both Headquarters and RTP.

    - This task order ends 4/30/25, it will not be renewed

Jan. 2026 PC (Laptops) Refresh (Kim)

Wednesday, January 28, 2026

3:11 PM

  - Current POP Expiration:   - A.R.O. 45 days

  - Ultimate Contract Expiration:

  - Contract Number:  68HERF26F0048

  - COR:  Kim Farmer

  - CO/CS:  Ross Gillingham

  - Status:  On Track

  - Current Updates:

    - 3/17:  Fully awarded Contract # 68HERF26F0048.

  - Past Updates:

    - 1/27:  EO Compliance form was submitted for approval in the amount of $$2,674,940.46.  COR is completing other documentation that is required for PR.

    - 2/11/26 Tech office submitted revised IGCE increasing cost to $2,704,288.86

    - 2/12/26 revised compliance memo submitted for additional cost

    - 2/13/26 approved Compliance memo for increase received.

    - 2/17/26 PR-OFA-26-00301 submitted to FCO.